## 1. PRE-FEASIBILITY
CONSTRUCTION PRE-FEASIBILITY STUDY – RESIDENTIAL PROJECT
CERROS DE SUBA ¦ Bogotá D.C. ¦ Prepared: June 2026 ¦ Figures in USD (Exchange Rate: $4,200 COP)
Colombian Financial Reporting Standard NIF A-1 / IAS 11 ¦ CTCP Conceptual Framework ¦ Decree 2420/2015
MODEL PARAMETERS AND ASSUMPTIONS
Exchange Rate (COP/USD) – Ref. June 2026 |  |  |  | 4200
Discount Rate (estimated WACC) |  |  |  | 12%
Projected Annual Inflation (CPI) |  |  |  | 6.5%
Projection Horizon |  |  |  | 24 months
Corporate Income Tax Rate (2026) |  |  |  | 35%
Number of Residential Units |  |  |  | 92
Parking Spaces with Storage Unit |  |  |  | 110
Terraces |  |  |  | 18
Total Built Area (m²) |  |  |  | 23890.34
Total Saleable Area (m²) |  |  |  | 21919.6
Average Unit Area (m²) |  |  |  | 238.257
Price per m² – apartment |  |  |  | USD 2,380.95
Price per parking space with storage |  |  |  | USD 14,285.71
Unit Price – Terrace |  |  |  | USD 952.38
Construction Cost Adjustment Factor 2026 (−10%) |  |  |  | -10%
Ch. | Item | CONCEPT / CATEGORY | % of Sales | AMOUNT (USD) | USD/m² Built | USD/m² Saleable | COP (ref.)
1 | 1. ESTIMATED SALES REVENUE
1 | 1.1 | Apartment sales (92 units × 238.257 m² × USD 2,380.95/m²) | 97.05% | 52189628.5714 | 2184.5494 | 2380.9572 | 219196440000
1 | 1.2 | Parking spaces with storage (110 units × USD 14,285.71) | 2.922% | 1571428.5714 | 65.7767 | 71.6906 | 6600000000
1 | 1.3 | Terrace sales (18 units × USD 952.38) | 0.03188% | 17142.8571 | 0.71756 | 0.78208 | 72000000
TOTAL BUDGETED SALES REVENUE |  |  | 100% | 53778200 | 2251.0437 | 2453.4298 | 225868440000
2 | 2. DIRECT CONSTRUCTION COSTS (−10% adjustment applied)
2 | 2.1 | Shell & core, structure and mechanical/electrical/plumbing rough-in | 4.998% | 2687663.25 | 112.5 | 122.6146 | 11288185650
2 | 2.2 | Finishes and fit-out | 3.284% | 1766178.7071 | 73.9286 | 80.5753 | 7417950570
2 | 2.3 | Equipment and furnishings | 0.271% | 145714.2857 | 6.0993 | 6.6477 | 612000000
2 | 2.4 | Vehicular roads and driveways | 1.048% | 563508 | 23.5873 | 25.708 | 2366733600
2 | 2.5 | Pedestrian walkways and pavements | 0.09475% | 50957.115 | 2.133 | 2.3247 | 214019883
2 | 2.6 | Parks and green areas | 1.202% | 646374 | 27.0559 | 29.4884 | 2714770800
2 | 2.7 | Common service areas | 1.693% | 910588.7143 | 38.1154 | 41.5422 | 3824472600
2 | 2.8 | Semi-basements / Parking levels | 1.196% | 643082.1429 | 26.9181 | 29.3382 | 2700945000
2 | 2.9 | Water supply networks | 0.07172% | 38571.4286 | 1.6145 | 1.7597 | 162000000
2 | 2.10 | Sewage and drainage networks | 0.05479% | 29464.2857 | 1.2333 | 1.3442 | 123750000
2 | 2.11 | Gas supply networks | 0.0767% | 41250 | 1.7266 | 1.8819 | 173250000
2 | 2.12 | Electrical networks | 0.02391% | 12857.1429 | 0.53817 | 0.58656 | 54000000
2 | 2.13 | Telecommunications networks | 0.01315% | 7071.4286 | 0.296 | 0.32261 | 29700000
Subtotal direct construction costs |  |  |  | 7543280.5007 | 315.7461 | 344.134 | 31681778103
2 | 2.14 | Construction management fees (7% of adjusted direct costs) | 0.9819% | 528029.6351 | 22.1022 | 24.0894 | 2217724467.21
TOTAL DIRECT CONSTRUCTION COSTS |  |  | 15.01% | 8071310.1358 | 337.8483 | 368.2234 | 33899502570.21
3 | 3. INDIRECT CONSTRUCTION COSTS (−10% adjustment applied)
3 | 3.1 | Building and urban development permits | 0.4803% | 258281.9241 | 10.8111 | 11.7831 | 1084784081.4
3 | 3.2 | Insurance policies | 0.04503% | 24214.0599 | 1.0136 | 1.1047 | 101699051.4
3 | 3.3 | Utility connection fees | 0.03752% | 20178.2754 | 0.84462 | 0.92056 | 84748756.5
3 | 3.4 | Topographic survey | 0.01195% | 6428.5714 | 0.26909 | 0.29328 | 27000000
3 | 3.5 | Geotechnical / soil study | 0.06375% | 34285.7143 | 1.4351 | 1.5642 | 144000000
3 | 3.6 | Architectural design fees | 0.4735% | 254637.4389 | 10.6586 | 11.6169 | 1069477243.2
3 | 3.7 | Urban design fees | 0.6894% | 370732.6251 | 15.5181 | 16.9133 | 1557077025.6
3 | 3.8 | Structural engineering fees | 0.07969% | 42857.1429 | 1.7939 | 1.9552 | 180000000
3 | 3.9 | Hydraulic and sanitary engineering fees | 0.04383% | 23571.4286 | 0.98665 | 1.0754 | 99000000
3 | 3.10 | HVAC and mechanical ventilation design fees | 0.03387% | 18214.2857 | 0.76241 | 0.83096 | 76500000
3 | 3.11 | Security systems design fees | 0.05379% | 28928.5714 | 1.2109 | 1.3198 | 121500000
3 | 3.12 | Project budgeting and scheduling | 0.01195% | 6428.5714 | 0.26909 | 0.29328 | 27000000
3 | 3.13 | Construction supervision and inspection fees | 0.3752% | 201782.7534 | 8.4462 | 9.2056 | 847487564.1
3 | 3.14 | Condominium by-laws and property appraisals | 0.03985% | 21428.5714 | 0.89696 | 0.9776 | 90000000
TOTAL INDIRECT CONSTRUCTION COSTS |  |  | 2.44% | 1311969.9339 | 54.9163 | 59.8537 | 5510273722.2
4 | 4. FIDUCIARY, ADMINISTRATIVE & OTHER COSTS (no discount applied)
4 | 4.1 | Pre-sales escrow trust (fiducia previa) | 0.01404% | 7551.0631 | 0.31607 | 0.34449 | 31714465
4 | 4.2 | Escrow trust management fee | 0.1705% | 91688.5714 | 3.8379 | 4.1829 | 385092000
4 | 4.3 | Legal advisory fees | 0.02436% | 13098.3679 | 0.54827 | 0.59756 | 55013145
4 | 4.4 | Tax advisory fees | 0.02436% | 13098.3679 | 0.54827 | 0.59756 | 55013145
4 | 4.5 | Accounting advisory fees | 0.03653% | 19647.5519 | 0.82241 | 0.89635 | 82519718
4 | 4.6 | Banking and financial charges | 0.1624% | 87322.4533 | 3.6551 | 3.9838 | 366754304
4 | 4.7 | General administrative expenses | 0.4871% | 261967.36 | 10.9654 | 11.9513 | 1100262912
4 | 4.8 | Property management prior to handover | 0.4871% | 261967.36 | 10.9654 | 11.9513 | 1100262912
4 | 4.9 | Notary and deed registration costs | 0.2436% | 130983.68 | 5.4827 | 5.9756 | 550131456
4 | 4.10 | Property tax during construction | 0.2218% | 119285.7143 | 4.9931 | 5.442 | 501000000
TOTAL FIDUCIARY, ADMINISTRATIVE & OTHER COSTS |  |  | 1.872% | 1006610.4898 | 42.1346 | 45.9228 | 4227764057
5 | 5. FINANCING COSTS
5 | 5.1 | Estimated construction loan amount | 0% | 0 | 0 | 0 | 0
5 | 5.2 | Construction loan interest charges | 0% | 0 | 0 | 0 | 0
TOTAL FINANCING COSTS |  |  | 0% | 0 | 0 | 0 | 0
6 | 6. PROFESSIONAL FEES, SALES & MARKETING (no discount applied)
6 | 6.1 | Financial structuring fees (2.5% of sales) | 2.5% | 1344455 | 56.2761 | 61.3357 | 5646711000
6 | 6.2 | Project management fees (2.5% of sales) | 2.5% | 1344455 | 56.2761 | 61.3357 | 5646711000
6 | 6.3 | Sales commission (3.0% of sales) | 3% | 1613346 | 67.5313 | 73.6029 | 6776053200
6 | 6.4 | Marketing, advertising & sales office (2.0% of sales) | 2% | 1075564 | 45.0209 | 49.0686 | 4517368800
TOTAL FEES, SALES & MARKETING |  |  | 10% | 5377820 | 225.1044 | 245.343 | 22586844000
7 | 7. LAND ACQUISITION COST (no discount applied)
7 | 7.1 | Land purchase cost (25% of total sales) | 25% | 13444550 | 562.7609 | 613.3575 | 56467110000
TOTAL LAND ACQUISITION COST |  |  | 25% | 13444550 | 562.7609 | 613.3575 | 56467110000
PROJECT OVERALL SUMMARY
1 | ESTIMATED SALES REVENUE |  | 100% | 53778200 | 2251.0437 | 2453.4298 | 225868440000
2 | Direct construction costs (−10%) |  | 15.01% | 8071310.1358 | 337.8483 | 368.2234 | 33899502570.21
3 | Indirect construction costs (−10%) |  | 2.44% | 1311969.9339 | 54.9163 | 59.8537 | 5510273722.2
4 | Fiduciary, administrative & other costs |  | 1.872% | 1006610.4898 | 42.1346 | 45.9228 | 4227764057
5 | Financing costs |  | 0% | 0 | 0 | 0 | 0
6 | Fees, sales & marketing |  | 10% | 5377820 | 225.1044 | 245.343 | 22586844000
7 | Land acquisition cost (25%) |  | 25% | 13444550 | 562.7609 | 613.3575 | 56467110000
TOTAL PROJECT COSTS |  |  | 54.32% | 29212260.5594 | 1222.7645 | 1332.7004 | 122691494349.41
GROSS PROFIT BEFORE TAXES |  |  | 45.68% | 24565939.4406 | 1028.2792 | 1120.7294 | 103176945650.59

## 2. TAXES & DEDUCTIONS
TAXES, DEDUCTIONS & SALES ANALYSIS – COLOMBIAN FINANCIAL REPORTING STANDARDS
Project: Cerros de Suba – Bogotá ¦ Figures in USD (Exchange Rate $4,200 COP) ¦ June 2026
A. SALES REVENUE BREAKDOWN (IFRS 15)
CONCEPT | UNITS | UNIT VALUE (USD) | TOTAL (USD) | % of Sales | COP REFERENCE
Apartments (92 units × 238.257 m² × USD 2,380.95/m²) | 92 | 567278.5714 | 52189628.5714 | 97.05% | 219196440000
Terraces (18 units) | 18 | 952.381 | 17142.8571 | 0.03188% | 72000000
Parking spaces with storage (110 units) | 110 | 14285.7143 | 1571428.5714 | 2.922% | 6600000000
TOTAL GROSS REVENUE | 220 |  | 53778200 | 100% | 225868440000
B. SIMPLIFIED INCOME STATEMENT & TAXES (IAS 12 / Art. 240 Tax Code)
CONCEPT | RATE | AMOUNT (USD) | COP (reference) | % of Sales | NOTE
Gross sales revenue |  | 53778200 | 225868440000 | 100% | IFRS 15
(−) Total project costs |  | 29212260.5594 | 122691494349.41 | 54.32% | CAPEX + OPEX
GROSS PROFIT BEFORE TAXES |  | 24565939.44 | 103176945650.59 | 45.68% | 45.7% of sales
(−) Corporate Income Tax (35% on gross profit) | 35% | 8598078.8042 | 36111930977.7065 | 15.99% | Art. 240 Tax Code – Law 2010/2019
(−) Withholding Tax on sales (1%) | 1% | 537782 | 2258684400 | 1% | Art. 401 Tax Code
(−) Municipal Trade Tax Withholding – Reteica (0.33% of revenue) | 0.33% | 177468.06 | 745365852 | 0.33% | Agreement 65/2002 – Bogotá
(−) Municipal Industry & Commerce Tax – ICA (0.33%) | 0.33% | 177468.06 | 745365852 | 0.33% | Law 14/1983
TOTAL TAX BURDEN |  | 9490796.92 | 39861347081.7065 | 17.65% | 17.65% of sales
NET PROJECT PROFIT |  | 15075142.52 | 63315598568.8837 | 28.03% | Net margin: 28.03%

## 3. EXECUTIVE SUMMARY
CERROS DE SUBA – EXECUTIVE SUMMARY
Pre-Feasibility Study June 2026 ¦ Figures in USD ¦ Exchange Rate $4,200 COP/USD ¦ Colombian IFRS
REVENUE
Total budgeted sales revenue | USD 53,778,200 | COP 225,868,440,000
Average price per apartment | USD 567,279 | COP 2,382,570,000
Price per m² – apartment | USD 2,380.95/m² | COP 10,000,000/m²
Price per parking space with storage | USD 14,285.71 | COP 60,000,000
COSTS
Direct construction (−10% 2026 adjustment) | USD 8,071,310 | 15.0% of sales
Indirect construction (−10% 2026 adjustment) | USD 1,311,970 | 2.4% of sales
Fiduciary & administrative costs | USD 1,006,610 | 1.9% of sales
Fees, sales & marketing | USD 5,377,820 | 10.0% of sales
Land acquisition (25% of sales) | USD 13,444,550 | 25.0% of sales
TOTAL COSTS | USD 29,212,261 | 54.3% of sales
RESULTS
Gross profit before taxes | USD 24,565,939 | Gross margin: 45.7%
Total tax burden | USD 9,490,797 | 17.65% of sales
NET PROJECT PROFIT | USD 15,075,143 | Net margin: 28.03%
COP equivalent (Exchange Rate $4,200) | COP 63,315,598,569
KEY PERFORMANCE INDICATORS
Project ROI | 51.61% | Return on total investment
Break-even point | 54.3% of sales | Total costs / Total sales
TECHNICAL DATA
Residential units | 92 apartments
Parking Spaces with Storage Unit | 110 units
Terraces | 18 units
Total built area | 23,890.34 m²
Total saleable area | 21,919.60 m²
Saleable / built area ratio | 91.75% | 91.75%
Exchange rate applied | USD 1 = COP 4,200 | Reference June 2026